## Sheet1
Day | time axis 2020-04-20 to 2020-06-12
Activity | Done
Research preparation
Introduction BEP | v | bar: 2020-04-20
Preparing digital environment | v | 2020-04-21: Install Windows; 2020-04-23: Configure Environment; 2020-04-26: Install D-Flow FM
Problem definition | v | bar: 2020-04-22 to 2020-05-04
Define objective & questions | t | bar: 2020-04-22 to 2020-05-04
Define research strategy | t | 2020-04-22: Initial strategy based on literature research; 2020-05-11: Refinement of strategy based on first tests, reference model and mid-term meeting
Literature research | bar: 2020-04-20 to 2020-05-15
First simulations
Explore D-Flow FM | v | bar: 2020-05-04 to 2020-05-08
Define basic model | v | 2020-05-08: Lock-exchange geometry, physics, boundary conditions
Test different model parameters |  | 2020-05-09: Change number of layers and initial salinity difference
Post-processing |  | 2020-05-11: Plotting results and qualitative analysis of simulations
Define stable reference model | bar: 2020-05-08 to 2020-05-14
Data generation
Interval analysis |  | 2020-05-16: Define ranges for parameter variation
Python scripting simulation runs | bar: 2020-05-06 to 2020-05-20
Simulate spatial variations |  | 2020-05-18: Vary meshtype & resolution in x,y and z direction
Simulate temporal variations |  | 2020-05-22: Vary Courant number and timestep size
Simulate salinity variations |  | 2020-05-27: Vary initial salinity
Simulate other variations |  | 2020-06-01: Vary other parameters
Data analysis
Qualitative analysis of observation |  | 2020-05-10: Support iteration process
Generating plots per parameter |  | 2020-05-12: WHAT PLOTS?
Sensitivity analysis | bar: 2020-05-20 to 2020-05-21; 2020-05-26; 2020-05-29; 2020-06-03 to 2020-06-05
Evaluating indicator parameters | bar: 2020-05-13; 2020-05-20 to 2020-05-21; 2020-05-26; 2020-05-29; 2020-06-03 to 2020-06-05
Report & present
Write plan of action | bar: 2020-04-22 to 2020-05-04
Write mid-term report |  | 2020-05-06: Set up chapters; 2020-05-09: Log results; 2020-05-13: Finalize report
Create mid-term presentation | bar: 2020-05-14
Write final report | bar: 2020-05-16 to 2020-05-22; 2020-05-25 to 2020-05-29; 2020-06-01 to 2020-06-05; 2020-06-08 to 2020-06-11
Create final presentation | bar: 2020-06-10 to 2020-06-11